## Risk Assessment
Reference Number	Description	Evaluation	Likelihood	Impact Level	Responsibility	Response	Control Measures
1	Internet dropping	Developers losing internet connection, causing breaks in the workflow	Low	Low	Developers	Reconnect to internet and call, ensure team is in contact via other mediums to ensure work can continue.	Work near router, use ethernet cable when possible, reduce other machines using the router.
2	Team Member injury/illness	Loss of a team member due to injury and/or illness causing a disruption to the workflow.	High	Medium	Developers	Contact the group to inform them of your absence.	Ensure work is pushed to the repository reguarly, to enable other team members to pick up where you left off. Ensure pushes have detailed commit messages to clarify the state of progress.
3	Not meeting product owners brief/expectation.	Misunderstanding the products owners brief / expectation can result in the MVP not being met.	Low	Medium	Developers	Contact product owner to establish expectation and clarify the brief.	Contact the product owner to establish an initial MVP expectation and to clarify the brief to avoid any confusions. Set up regular meetings (every two days week one, daily week two), to update the product owner on the groups progress and to raise any questions and / or concerns.
4	Secure security group settings	Security groups should only allow access to the minimum necessary ports, passwords and credentials to be kept private.	Low	High	Developers	In the event of a security breach temporarily take down the EC2 and change the passwords. Evaluate security settings and improve where necessary.	Ensure passwords and credentials are kept private, ensure passwords are strong, put backend and databases in private networks, minimise port access on public networks to only those necessary.
5	Broken GitHub push	Deployed product may cause issues when merging	Medium	Medium	Developers	Revert production to most recent stable version	Automate tests before any deployment & restrict access to development branch. Ensure pier reviews are enforced for merges.
6	Application's virtual machine goes down	Application goes offline	Low	High	AWS	Recreate infrastucture on another machine	Use infrastructure as code to quickly recreate machine & store all code in VCS
7	Application’s virtual machine is overwhelmed	Application’s virtual machine is unable to keep up with demand.	Medium	High	Developers	Application scales up and down as needed.	Auto scaling groups with suitable CPU, selection of an appropriate initial size EC2.
8	Data set size affecting applications effectiveness.	Large data set may cause optimisation issue, causing the application to fall over, or take too long to answer data requests	High	Low	Developers	Review algorithms.	Ensure EC2 are created with sufficient initial size, and increased in size if required.

## Incident Report
Date	Incident	Effect	Response	Result
20/09/21	LF-H medical incident	Unable to attend workday	LF-H – contact Group3 ASAP, so that they can reasign the workload planned for that day. / Group3 - Ensure workday is well documented on Jira, and regular Git commits are detailed to ensure progress is clear and available to all team members.	No disruption to workflow
20/09/21	KB called out for one-to-one		KB kept one-to-one short, and ensured the meeting was taken when her absence would cause the least impact to the workflow.	Minimal disruption
21/09/21	LF-H medical incident	Unable to attend workday	LF-H – contact Group3 ASAP, so that they can reasign the workload planned for that day. / Group3 - Ensure workday is well documented on Jira, and regular Git commits are detailed to ensure progress is clear and available to all team members.	No disruption to workflow
22/09/21	LF-H medical incident	Unable to attend workday	LF-H – contact Group3 ASAP, so that they can reasign the workload planned for that day. / Group3 - Ensure workday is well documented on Jira, and regular Git commits are detailed to ensure progress is clear and available to all team members.	No disruption to workflow
23/09/21	LF-H medical incident	Unable to attend workday	LF-H – contact Group3 ASAP, so that they can reasign the workload planned for that day. / Group3 - Ensure workday is well documented on Jira, and regular Git commits are detailed to ensure progress is clear and available to all team members.	No disruption to workflow
24/09/21	LF-H medical incident	Unable to attend workday	LF-H – contact Group3 ASAP, so that they can reasign the workload planned for that day. / Group3 - Ensure workday is well documented on Jira, and regular Git commits are detailed to ensure progress is clear and available to all team members.	No disruption to workflow
27/09/21	LF-H medical incident	Unable to attend workday	LF-H – contact Group3 ASAP, so that they can reasign the workload planned for that day. / Group3 - Ensure workday is well documented on Jira, and regular Git commits are detailed to ensure progress is clear and available to all team members.	No disruption to workflow
27/09/21	DM work meeting p.m.	Unable to attend project p.m. workday	DM - contact Group3 ASAP, so that they can reasign the workload planned for that day. Ensure all work done to date it pushed to Git with smart commits so that team members can continue with essential work.	minimal disruption workflow
27/09/21	RD – medical incident	Unable to attend project p.m. workday	RD - contact Group3 ASAP, so that they can reasign the workload planned for that day. Ensure all work done to date it pushed to Git with smart commits so that team members can continue with essential work.	minimal disruption workflow
28/09/21	LF-H medical incident	Unable to attend workday	LF-H – contact Group3 ASAP, so that they can reasign the workload planned for that day. / Group3 - Ensure workday is well documented on Jira, and regular Git commits are detailed to ensure progress is clear and available to all team members.	No disruption to workflow